## Schedule Production
DRAFT Production Calendar | Winter 2023 | Spring 2023
| DUE | DUE
Tables Built | XXXXX | XXXXX
Schedule Roll | XXXXX | XXXXX
Master Division Schedule D1 distribution to Division Deans | 2022-07-05 | 2022-07-05
Group 1 (Library, Art, Kinesiology, CTE, Student Services) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | 2022-07-29 | 2022-07-29
Group 2 (Communications, Business, AJ/Fire) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | 2022-07-29 | 2022-07-29
Group 3 (BSS, MS&E, Health Science & Nursing) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | 2022-07-29 | 2022-07-29
Division Schedule D2 created for all divisions. Includes reassigned time, non-instructional assignments, special assignments, etc. | 2022-08-26 | 2022-08-26
Division Schedule D2 distribution to all divisions | 2022-08-26 | 2022-08-26
Division Schedule D2 corrections and updates completed by Deans and forwarded to I.O. Deans proof/correct CRN, terms, loads, space, assignment type, attendance accounting, and forward to instructional operations | 2022-09-09 | 2022-09-09
Final College Schedule distribution to all Deans (D3) | 2022-09-30 | 2022-09-30
Online schedule live (viewing only): Changes can be made to schedule until date listed. | 2022-10-10 | 2022-10-10
Textbook adoptions due | XXXXX | XXXXX
Load Sheets Prepared and verified for coding, load, and non-instructional assignments. Forward unsigned load sheets to I.O. | 2022-11-28 | 2022-11-28
Load Sheets submitted to Human Resources (no signature) | 2022-12-12 | 2022-12-12
Salary Sheets prepared | XXXXX | XXXXX
Final Load Sheets printed and signed. Forward signedload sheets to I.O. | 2022-12-12 | 2022-12-12
Registration begins (NO CHANGES) | 2022-10-31 | 2022-10-31
Changes/Updates/Additions/Cancellations to I.O. Thereafter, as needed to I.O. (unsigned okay for payroll purposes; cc: HR Cynthia Nuñez & Cindy Sanchez) | Ongoing | Ongoing
Instructional Operations forwards copies of revised load sheets to Divisions and Human Resources as changes occur (Signed load sheets immediately to follow) | Ongoing | Ongoing
All staffing must be COMPLETED (3 weeks before first day of term)
Cancel classes with <50% enrollment, unless approved by VPAA (3 weeks before first day of term)*
Cancel classes with <70% enrollment, unless approved by VPAA (1 week before first day of term)*
Session Begins
Overload and Part-Time Payroll
Grades Due
*work with VPAA re: any exceptions |  |  | rev. Draft 5/19/2022

## Win_Spr_Data (hidden)
Description | Tasks | Duration | Start Date | End Date
I/O prepare schedule distribution | I/O prepare D1 schedule | 19 | 2020-04-01 | 2020-04-20
Schedule roll out | D1 Schedule roll out | 0 | 2020-04-20 | 2020-04-20
Group 1 (Library, Art, Kinesiology, CTE, Student Services) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | G1 - D1 dean review | 27 | 2020-04-21 | 2020-05-18
Group 2 (Communications, Business, AJ/Fire) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | G2 - D1 dean review | 31 | 2020-04-21 | 2020-05-22
Group 3 (BSS, MS&E, Health Science & Nursing) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | G3 - D1 dean review | 45 | 2020-04-21 | 2020-06-05
Division Schedule D2 created for all divisions. Includes reassigned time, non-instructional assignments, special assignments, etc. | I/O prepare D2 schedule | 17 | 2020-06-05 | 2020-06-22
| D2 Schedule roll out | 0 | 2020-06-22 | 2020-06-22
Division Schedule D2 corrections and updates completed by Deans and forwarded to I.O. Deans proof/correct CRN, terms, loads, space, assignment type, attendance accounting, and forward to instructional operations | G1, G2, G3 - D2 dean review | 25 | 2020-06-22 | 2020-07-17
| I/O prepare D3 schedule | 21 | 2020-07-17 | 2020-08-07
Final College Schedule distribution to all Deans (D3) | D3 schedule roll out | 0 | 2020-08-07 | 2020-08-07
Load Sheets Prepared and verified for coding, load, and non-instructional assignments. Forward unsigned load sheets to I.O. | Load sheets prepared and verified | 70 | 2020-08-07 | 2020-10-16
| Prepare single load sheets | 86 | 2020-08-07 | 2020-11-01
Changes/Updates/Additions/Cancellations to I.O. Thereafter, as needed to I.O. (unsigned okay for payroll purposes; cc: HR Cynthia Nuñez & Cindy Sanchez) | Changes to HR / Copies to Divisions | 86 | 2020-08-07 | 2020-11-01
Online schedule live (viewing only): Changes can be made to schedule until date listed. | Online schedule viewing | 25 | 2020-10-01 | 2020-10-26
Load Sheets submitted to Human Resources (no signature) | Submit load sheets to HR | 0 | 2020-10-16 | 2020-10-16
Registration begins (NO CHANGES) | Registration begins | 0 | 2020-10-26 | 2020-10-26
Final Load Sheets printed and signed. Forward signedload sheets to I.O. | Forward single load sheets to I/O | 0 | 2020-11-01 | 2020-11-01
| All winter staffing done | 0 | 2020-12-07 | 2020-12-07
| Cancel winter classes with <50% enrollment | 0 | 2020-12-07 | 2020-12-07
| Cancel winter classes with <70% enrollment | 0 | 2020-12-21 | 2020-12-21
| All spring staffing done | 0 | 2021-01-04 | 2021-01-04
| Cancel spring classes with <50% enrollment | 0 | 2021-01-04 | 2021-01-04
| Cancel spring classes with <70% enrollment | 0 | 2021-01-19 | 2021-01-19

## SummerData (hidden)
Description | Tasks | Duration | Start Date | End Date
I/O prepare schedule distribution | I/O prepare D1 schedule distribution | 52 | 2020-09-01 | 2020-10-23
Schedule roll out | D1 Schedule roll out | 0 | 2020-11-02 | 2020-11-02
Group 1 (Library, Art, Kinesiology, CTE, Student Services) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | G1 - D1 dean review | 21 | 2020-11-02 | 2020-11-23
Group 2 (Communications, Business, AJ/Fire) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | G2 - D1 dean review | 28 | 2020-11-02 | 2020-11-30
Group 3 (BSS, MS&E, Health Science & Nursing) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | G3 - D1 dean review | 32 | 2020-11-02 | 2020-12-04
Division Schedule D2 created for all divisions. Includes reassigned time, non-instructional assignments, special assignments, etc. | I/O prepare D2 schedule distribution | 7 | 2020-12-04 | 2020-12-11
| D2 Schedule roll out | 0 | 2020-12-11 | 2020-12-11
Division Schedule D2 corrections and updates completed by Deans and forwarded to I.O. Deans proof/correct CRN, terms, loads, space, assignment type, attendance accounting, and forward to instructional operations | G1, G2, G3 - D2 dean review | 28 | 2020-12-11 | 2021-01-08
| I/O prepare D3 schedule distribution | 7 | 2021-01-08 | 2021-01-15
Final College Schedule distribution to all Deans (D3) | D3 schedule roll out | 0 | 2021-01-15 | 2021-01-15
Online schedule live (viewing only): Changes can be made to schedule until date listed. | Online schedule viewing | 32 | 2021-01-15 | 2021-02-16
Load Sheets Prepared and verified for coding, load, and non-instructional assignments. Forward unsigned load sheets to I.O. | Load sheets prepared and verified | 0
Load Sheets submitted to Human Resources (no signature) | Submit load sheets to HR | 0
| Prepare single load sheets | 0
Final Load Sheets printed and signed. Forward signedload sheets to I.O. | Forward single load sheets to I/O | 0
Registration begins (NO CHANGES) | Registration begins | 0 | 2021-03-08 | 2021-03-08
Changes/Updates/Additions/Cancellations to I.O. Thereafter, as needed to I.O. (unsigned okay for payroll purposes; cc: HR Cynthia Nuñez & Cindy Sanchez) | Changes to HR / Copies to Divisions | 0

## FallData (hidden)
Description | Tasks | Duration | Start Date | End Date
I/O prepare schedule distribution | I/O prepare D1 schedule distribution | 30 | 2020-11-15 | 2020-12-15
Schedule roll out | D1 Schedule roll out | 0 | 2020-12-15 | 2020-12-15
Group 1 (Library, Art, Kinesiology, CTE, Student Services) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | G1 - D1 dean review | 27 | 2020-12-15 | 2021-01-11
Group 2 (Communications, Business, AJ/Fire) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | G2 - D1 dean review | 38 | 2020-12-15 | 2021-01-22
Group 3 (BSS, MS&E, Health Science & Nursing) Deans update schedule and forward to Instructional Operations (Update 1) All full time assignments must be included | G3 - D1 dean review | 45 | 2020-12-15 | 2021-01-29
Division Schedule D2 created for all divisions. Includes reassigned time, non-instructional assignments, special assignments, etc. | I/O prepare D2 schedule distribution | 13 | 2021-01-29 | 2021-02-11
| D2 Schedule roll out | 0 | 2021-02-11 | 2021-02-11
Division Schedule D2 corrections and updates completed by Deans and forwarded to I.O. Deans proof/correct CRN, terms, loads, space, assignment type, attendance accounting, and forward to instructional operations | G1, G2, G3 - D2 dean review | 18 | 2021-02-11 | 2021-03-01
| I/O prepare D3 schedule distribution | 7 | 2021-03-01 | 2021-03-08
Final College Schedule distribution to all Deans (D3) | D3 schedule roll out | 0 | 2021-03-08 | 2021-03-08
Online schedule live (viewing only): Changes can be made to schedule until date listed. | Online schedule viewing | 56 | 2021-01-15 | 2021-03-12
Load Sheets Prepared and verified for coding, load, and non-instructional assignments. Forward unsigned load sheets to I.O. | Load sheets prepared and verified | 0
Load Sheets submitted to Human Resources (no signature) | Submit load sheets to HR | 0
| Prepare single load sheets | 0
Final Load Sheets printed and signed. Forward signedload sheets to I.O. | Forward single load sheets to I/O | 0
Registration begins (NO CHANGES) | Registration begins | 0 | 2021-04-05 | 2021-04-05
Changes/Updates/Additions/Cancellations to I.O. Thereafter, as needed to I.O. (unsigned okay for payroll purposes; cc: HR Cynthia Nuñez & Cindy Sanchez) | Changes to HR / Copies to Divisions | 0